## Space Segment (simplified ECSS)
Document |  |  | To be delivered in the cycle? (yes, yes, if applicable, no, Recommended) |  | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control | [7 empty] | Document definition reference | Comments
Reference | Title | Acronym | De-risking | Product Development | RR | PDR | CDR | TRR | QAR | IOCR | DCCR | FR
Management
S.MG1 | Configuration and Documentation Management Plan | CMDP | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-M-ST-40C, Annex A
S.MG2 | Risk Register | RR | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: Monthly and at each progress meeting/review | ECSS-M-ST-80C, Annex D
S.MG3 | Business Plan | BP | Yes | Yes | [8 empty] | template available at https://incubed.esa.int/list-documents/ | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG4 | Document List | DL | Yes | Yes | N | U | U | U | U | U | C | C | Self descriptive | List of all documents produced in the frame of the contract.
S.MG5 | Monthly Progress Report | MPR | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: Monthly | template available at https://incubed.esa.int/list-documents/ | A concise monthly progress report will be provided to the Agency before the end of each month.
S.MG6 | Minutes of the Meeting | MoM | Yes | Yes | [8 empty] | template available at https://incubed.esa.int/list-documents/ | Formal written minutes of meetings attended by the Agency will be agreed and, as far as possible, be signed and made available to the Agency at the end of the meeting. If this is not possible the minutes will be provided to the Agency no later than five working days from the date of the meeting. The minutes will, as a minimum, identify all agreements made and actions accepted during the meeting. The action item list will be included in the minutes and will be updated in accordance with the meeting outcome. Each action item will be assigned a unique identifier in the format X.Y, where X is the meeting number in which it originated and Y is the action number, starting from 1 at each meeting. | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG7 | Activity Web Page | AWP | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: At the first review meeting and current status updated at each progress meeting | template available at https://incubed.esa.int/list-documents/ | As part of the first review data package the Contractor shall produce a Activity Web Page which shall be suited for publication by ESA in the InCubed web site. As a minimum, an update of the paragraph called “Current Status” shall be provided at each milestone review together with the minutes of the review meeting. A final version of the Activity Web Page shall be provided together with the Final Report. This final version shall include a paragraph summarising the most significant achievements of the activity.
S.MG8 | Justification for non continuation | JFNC | Yes | No | [9 empty] | In the event that it is no longer proposed to continue with the development at the De-risking Cycle, the Contractor shall deliver a Justification Letter to the Agency. The Justification Letter shall set out the reasons (technical and/or commercial) for not continuing the development. | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR
S.MG9 | Digital Media | DM | Yes | Yes | [9 empty] | High-Resolution (>2 MB) Photographs or a video shall be delivered, shall be releasable to the public and shall be delivered in a format that can easily be processed electronically (e.g. not in PDF). | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG10 | CCN for follow-on Cycle(s) | CCN-FOC | Yes | No | [8 empty] | template available at https://incubed.esa.int/list-documents/ | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR
S.MG11 | Contract Achievements and Socio Economic Impact Questionnaire | CA-SEIQ | Yes | Yes | [8 empty] | Online questionnaire to be provided by the TO | It will be provided at the end of the contract and will contain: summary of the activities, technical and commercial achievement, a socio-economic impact assessment of the activity. Once a year for 5 years after the conclusion of the contract the Agency will send an online questionnaire to be filled in to monitor the commercial growth of the product developed | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG12 | Product Data Sheet | PDS | No | Yes | [9 empty] | A Product Data Sheet shall be issued: • For each hardware unit which has been developed and tested within the contract, providing the functional performances, budgets (for space: mass, power, volume) and environmental specifications. • For each software item which has been developed and tested within the contract, listing the main functions and the demonstrated performance parameters. | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG13 | Final Data Package | FDP | Yes | Yes | [9 empty] | Comprise a compilation of the most recent versions of all deliverable documents including Final Report | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG14 | Final Report | FREP | Yes | Yes | [8 empty] | template available at https://incubed.esa.int/list-documents/ | The Final Report shall be written in a concise form and shall describe the major achievements of the Contract The Final Report may be made available to all ESA Participating States. Therefore, if the Final Report includes commercially sensitive information, two (2) different versions of the Final Report shall be provided. The front cover of the Final Report shall contain the following text: “EUROPEAN SPACE AGENCY CONTRACT REPORT “The work described in this report was done under ESA contract. Responsibility for the contents resides in the author or organization that prepared it.” | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
Engineering
S.EN1 | User/Customer Needs and Requirements | UCNR | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | template available at https://incubed.esa.int/list-documents/ | Use only paragraph 2 of the RD template (2. User/Customer Needs and Requirements). These requirments shall then have a tracebility with the MRD
S.EN2 | Mission Requirements Document | MRD | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ESA-TECSPC-DRD-024324
S.EN3 | Mission Analysis Report | MAR | Yes | Yes | N | U | U | U | U |  | C | C | ESA-TECSPC-DRD-024324
S.EN4 | System Requirements Document | SRD | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ESA-TECSPC-DRD-024324
S.EN5 | System Design Report | SDR | Yes | Yes | N | U | U |  |  |  | C | C | ESA-TECSPC-DRD-024324
S.EN6 | Environmental Design Specification | EDS | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ESA-TECSPC-DRD-024324
S.EN7 | Space Debris Mitigation Document | SBMD | Yes | Yes | N | U | U | U | U |  | C | C | ESA-TECSPC-DRD-024324
S.EN8 | Space-to-ground Interface Control Document | SGICD | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ESA-TECSPC-DRD-024324
S.EN9 | Declared Lists for Parts, Materials and Processes | DLs | Yes | Yes |  | N | U |  | U |  | C | C | ESA-TECSPC-DRD-024324
S.EN10 | Satellite Mechanical Analysis Report | SMAR | Yes | Yes |  | N | U | U | U |  | C | C | ESA-TECSPC-DRD-024324 | Could be merged in a single document with S.EN11, S.EN12 and S.EN13 or within S.EN5
S.EN11 | Satellite Thermal Analysis Report | STAR | Yes | Yes |  | N | U | U | U |  | C | C | ESA-TECSPC-DRD-024324 | Could be merged in a single document with S.EN10, S.EN12 and S.EN13 or within S.EN5
S.EN12 | Satellite AOCS Analysis Report | SAAR | Yes | Yes |  | N | U | U | U |  | C | C | ESA-TECSPC-DRD-024324 | Could be merged in a single document with S.EN10, S.EN11 and S.EN13 or within S.EN5
S.EN13 | Spacecraft Power Analysis Report | SPAR | Yes | Yes |  | N | U | U | U |  | C | C | ESA-TECSPC-DRD-024324 | Could be merged in a single document with S.EN.10, S.EN.11 and S.EN.12
S.EN14 | COTS User Manuals | COTsUM | Yes | Yes | [8 empty] | ESA-TECSPC-DRD-024324 | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.EN15 | System Development Plan | SDP | Yes | Yes | N | U | U |  |  |  | C | C | ESA-TECSPC-DRD-024324
S.EN16 | Payload-Platform Interface Control Document | ICD | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ESA-TECSPC-DRD-024324
S.EN17 | Launcher Interface Requirements Document | LIRD | Yes, if applicable | Yes | [8 empty] | ESA-TECSPC-DRD-024324 | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.EN18 | Mission Operations Plan | MOP | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ESA-TECSPC-DRD-024324
Testing
S.TE1 | Spacecraft AIV Plan | AIVP | Yes | Yes |  | N | U | U | U |  | C | C | ECSS-E-ST-10-03C, Annex A | Also available at TEC-SY/127/2013/DRD/RW
S.TE2 | Engineering Model Test Procedures | EMTP | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-10-03C, Annex B | Also available at TEC-SY/127/2013/DRD/RW
S.TE3 | Engineering Model Test Reports | EMTR | Yes, if applicable | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-10-03C, Annex C | Also available at TEC-SY/127/2013/DRD/RW
S.TE4 | System Verification Control Matrix | VCM | Yes, if applicable | Yes |  |  | N | U | U |  | C | C | ESA-TECSPC-DRD-024324
S.TE5 | Safety Data Package | SDP | No | Yes |  | N | U | U | U |  |  | C | ESA-TECSPC-DRD-024324
S.TE6 | Satellite Integration Logbook | SILB | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ESA-TECSPC-DRD-024324
S.TE7 | Satellite Proto-Flight Model Test Procedures | SPTP | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-10-03C, Annex B | Also available at TEC-SY/127/2013/DRD/RW
S.TE8 | Satellite Proto-Flight Model Test Reports | SPTR | No | Yes | [8 empty] | ECSS-E-ST-10-03C, Annex C | Also available at TEC-SY/127/2013/DRD/RW | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.TE9 | Ground Segment Acceptance Test Procedure | GSTP | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-10-03C, Annex B | Also available at TEC-SY/127/2013/DRD/RW
S.TE10 | Ground Segment Acceptance Test Report | GSTR | No | Yes | [8 empty] | ECSS-E-ST-10-03C, Annex C | Also available at TEC-SY/127/2013/DRD/RW | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.TE11 | System End-to-End Test Procedure | SEPP | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-10-03C, Annex B | Also available at TEC-SY/127/2013/DRD/RW
S.TE12 | System End-to-End Test Report | SETR | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control IOCR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-10-03C, Annex C | Also available at TEC-SY/127/2013/DRD/RW
S.TE13 | Mission Operations Status Reports | MOSR | No | Yes | [8 empty] | ESA-TECSPC-DRD-024324 | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control IOCR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.TE14 | In Orbit Commisioning Report | IOCR | No | [9 empty] | ECSS-M-ST-10C | The In-Orbit Commissioning Report is the main deliverable for the IOC Review, which is held at the end of the commissioning phase as part of the in‐orbit stage verification. It allows declaring readiness of the system for routine operations/utilization. This report contains the results of a series of on‐orbit tests properly designed to verify that all elements of the system (platform, payload and ground segment) are performing within the specified performance parameters. This report shall include the results of the platform test campaign, the outcomes of the calibration/validation campaign on the payload system as well as the evidence that the data products are compliant with the initial specifications. In case of a Pilot Phase to be carried out after the successful completion of the IOCR, the In-Orbit Commissioning Report shall be updated with the results of the Validation Campaign, in accordance to the plan in S.TE16. | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control IOCR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.TE15 | Post-flight Analysis Report | PFAR | No | Yes | [8 empty] | ESA-TECSPC-DRD-024324 | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control IOCR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.TE16 | Validation Plan | VP | No | Yes | [8 empty] | template available at https://incubed.esa.int/list-documents/ | With Validation Activities (a Pilot with the users/customers e.g. providing them L2/L3/L4 data products and getting their feedback) after the end of the commisioning phase (e.g. at IOCR) 1) Describe the entities involved in the operational use of the product (e.g. users/customers), at CDR 2) identify their role during the validation activities (a confirmation from them of their agreement to participate shall be provided in the proposal), at CDR 3) describe the approach to evaluate the success of the validation activities (e.g. identify measurable KPIs derived from on agreed validation activities objectives) at IOCR and start the pilot activities 4)Results of the validation activities, Intermediate reports shall be delivered on a weekly basis during the pilot (validation) activity providing visibility on the measures of the agreed KPIs (usually gathered from/with users) at FR | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control IOCR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
Product Assurance
S.PA2 | Quality Assurance Plan | QAP | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-Q-ST-10C, Annex A | Also available at TEC-SY/129/2013/SPD/RW
S.PA3 | Critical Item List | CIL | Yes | Yes |  | N | U | U | U |  | C | C | ECSS-Q-ST-10-04C, Annex A
S.PA4 | Configuration Item Data List | CIDL | No | Yes |  | N | U | U | U |  |  | C | ECSS-M-ST-40C, Annex C
S.PA5 | As-built Configuration List | ABCL | No | Yes | [8 empty] | ECSS-M-ST-40C, Annex D | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.PA6 | Qualification Status List | QSL | Yes | Yes |  | N | U | U | U |  |  | C | ECSS-Q-ST-10C, Annex B
S.PA7 | Cleanliness and contamination control plan | CCCP | No | Yes, if applicable | [8 empty] | ECSS-Q-ST-70-01C, Annex B | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.PA8 | Worst-Case Analysis | WCA | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-Q-ST-30C, Annex J
S.PA9 | Safety analysis | SA | No | Recommended |  | N | U | U | U |  |  | C | ECSS-Q-ST-40C, Annex C
S.PA10 | Radiation analysis | RA | Recommended | Recommended | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-Q-ST-60-15C, Annex B
S.PA11 | Request For Deviation | RFD | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: As needed | ECSS-M-ST-40C, Annex I
S.PA12 | Request For Waiver | RFW | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: As needed | ECSS-M-ST-40C, Annex J
S.PA13 | Non-Conformance Report | NCR | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: Within 48 hours of occurrence | ECSS-Q-ST-10-09C, Annex A
S.PA14 | End-Item Data Package | EIDP | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-Q-ST-20C, Annex B ECSS-Q-ST-20C, Annex C ECSS-Q-ST-20C, Annex D
S.PA15 | Single Event Phenomena Rates Calculation | SEPRC | No | Recommended |  | N | U | U | U |  |  | C | ECSS-Q-ST-60-15C, Annex B
S.PA16 | RFD / RFW List | RFD-RFW | No | Yes |  | N | U | U | U |  |  | C | Self descriptive
Software
S.SW1 | Software Configuration File | SCF | Yes, if applicable | Yes, if applicable |  | N | U | U | U |  | C | C | ECSS-M-ST-40C, Annex E | If applicable.
S.SW2 | Software Product Assurance Plan | SPAP | Yes, if applicable | Yes, if applicable |  | N | U |  | U |  | C | C | ECSS-Q-ST-80C, Annex B | If applicable.
S.SW3 | Software Requirements Specification | SRS | Yes, if applicable | Yes, if applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-40C, Annex D | If applicable.
S.SW4 | Software Interface Control Document | SICD | Yes, if applicable | Yes, if applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-40C, Annex E | If applicable.
S.SW5 | Software Design Document | SDD | Yes, if applicable | Yes, if applicable | N | U | U |  |  |  | C | C | ECSS-E-ST-40C, Annex F | If applicable.
S.SW6 | Software Release Document | SrelD | No | Yes, if applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control IOCR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-40C, Annex G | If applicable.
S.SW7 | Software User Manual | SUM | No | Yes, if applicable |  |  | N | U | U | U |  | C | ECSS-E-ST-40C, Annex H | If applicable.
S.SW8 | Software Verification Plan | SVerP | Yes, if applicable | Yes, if applicable | N | U | U | U |  |  | C | C | ECSS-E-ST-40C, Annex I | If applicable.
S.SW9 | Software Validation Plan | SValP | Yes, if applicable | Yes, if applicable | N | U | U | U |  |  | C | C | ECSS-E-ST-40C, Annex J | If applicable.
S.SW10 | Software Unit or Integration Test Plan | SUITP | Yes, if applicable | Yes, if applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-40C, Annex K | If applicable.
S.SW11 | Software Validation Specification | SVS | No | Yes, if applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-40C, Annex L | If applicable.
S.SW12 | Software Verification Report | SVR | No | Yes, if applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control IOCR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-40C, Annex M | If applicable.
S.SW13 | Software Validation Report | SVAR | No | Yes, if applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QAR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control IOCR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C | ECSS-E-ST-40C, Annex M | If applicable.
S.SW13 | Software Development Plan | SDP | Yes, if applicable | Yes, if applicable | N | U | U |  |  |  | C | C | ECSS-E-ST-40C, Annex O | If applicable.
S.SW14 | Software Configuration Management Plan | SCMP | Yes, if applicable | Yes, if applicable | N | U | U |  |  |  | C | C | ECSS-M-ST-40C, Annex A | If applicable.
S.SW15 | Software Reuse File | SRF | Yes, if applicable | Yes, if applicable |  | N | U | U |  |  | C | C |  | The Software Reuse File, if relevant, shall contain an analysis of existing software intended to be reused. The SRF shall be composed of the following two sections: Section 1, dedicated to present the analysis carried out to decide about the reuse (or not) of existing software taking into account the technical, operational and commercial requirements of the project. Furthermore the analysis shall cover the way the reused software will be embedded and/or integrated with the software to be developed in the project. The reused software shall be described in accordance with the information listed below (SRF List). Section 2, to characterize the deliverable software in terms of its constituent elements and the associated licensing schemes. The deliverable software (i.e. including developed and existing reused software) shall be described in accordance with the information listed below (SRF List): • software item name and main features; • developer name; • considered version and list of components; • licensing conditions; e.g. industrial property and exportability constraints, if any; • implementation language; • development and execution environment (e.g. platform, operating system); • applicable dispositions for warranty, maintenance, installation and training; • commercial software necessary for software execution, if any; • size of the software (e.g. number of source code lines, and size of the executable code)

## Space Segment (ECSS)
Document |  |  | To be delivered in the cycle? (yes, yes, if applicable, no, Recommended) |  | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control | [15 empty] | Document definition reference | Comments
Reference | Title | Acronym | De-risking | Product Development | MTR | RR | PDR | CDR | TRR | TRB | EQSR | QR | MRR | PAR | AR | CRR | SAT | DCCR | FR
Management
S.MG1 | Configuration and Documentation Management Plan | CMDP | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control SAT: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-M-ST-40C, Annex A
S.MG2 | Risk Register | RR | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: Monthly and at each progress meeting |  | ECSS-M-ST-80C, Annex D
S.MG3 | Business Plan | BP | Yes | Yes | [16 empty] | template available at https://incubed.esa.int/list-documents/ | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG4 | Document List | DL | Yes | Yes | [15 empty] | U | Self descriptive | List of all documents produced in the frame of the contract. | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG5 | Monthly Progress Report | MPR | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: Monthly |  | template available at https://incubed.esa.int/list-documents/ | A concise monthly progress report will be provided to the Agency within before the end of each month.
S.MG6 | Minutes of the Meeting | MoM | Yes | Yes | [16 empty] | template available at https://incubed.esa.int/list-documents/ | Formal written minutes of meetings attended by the Agency will be agreed and, as far as possible, be signed and made available to the Agency at the end of the meeting. If this is not possible the minutes will be provided to the Agency no later than five working days from the date of the meeting. The minutes will, as a minimum, identify all agreements made and actions accepted during the meeting. The action item list will be included in the minutes and will be updated in accordance with the meeting outcome. Each action item will be assigned a unique identifier in the format X.Y, where X is the meeting number in which it originated and Y is the action number, starting from 1 at each meeting. | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG7 | Activity Web Page | AWP | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: At the first review meeting and current status updated at each progress meeting |  | template available at https://incubed.esa.int/list-documents/ | As part of the first review data package the Contractor shall produce a Activity Web Page which shall be suited for publication by ESA in the InCubed web site. As a minimum, an update of the paragraph called “Current Status” shall be provided at each milestone review together with the minutes of the review meeting. A final version of the Activity Web Page shall be provided together with the Final Report. This final version shall include a paragraph summarising the most significant achievements of the activity.
S.MG8 | Justification for non continuation | JFNC | Yes | No | [17 empty] | In the event that it is no longer proposed to continue with the development at the De-risking Cycle, the Contractor shall deliver a Justification Letter to the Agency. The Justification Letter shall set out the reasons (technical and/or commercial) for not continuing the development. | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR
S.MG9 | Digital Media | DM | Yes | Yes | [17 empty] | High-Resolution (>2 MB) Photographs or a video shall be delivered, shall be releasable to the public and shall be delivered in a format that can easily be processed electronically (e.g. not in PDF). | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG10 | CCN for follow-on Cycle(s) | CCN-FOC | Yes | No | [16 empty] | template available at https://incubed.esa.int/list-documents/ | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR
S.MG11 | Contract Achievements and Socio Economic Impact Questionnaire | CA-SEIQ | Yes | Yes | [16 empty] | Online questionnaire to be provided by the TO | It will be provided at the end of the contract and will contain: summary of the activities, technical and commercial achievement, a socio-economic impact assessment of the activity. Once a year for 5 years after the conclusion of the contract the Agency will send an online questionnaire to be filled in to monitor the commercial growth of the product developed | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG12 | Product Data Sheet | PDS | No | Yes | [17 empty] | A Product Data Sheet shall be issued: • For each hardware unit which has been developed and tested within the contract, providing the functional performances, budgets (for space: mass, power, volume) and environmental specifications. • For each software item which has been developed and tested within the contract, listing the main functions and the demonstrated performance parameters. | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG13 | Final Data Package | FDP | Yes | Yes | [17 empty] | Comprise a compilation of the most recent versions of all deliverable documents including Final Report | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.MG14 | Final Report | FREP | Yes | Yes | [16 empty] | template available at https://incubed.esa.int/list-documents/ | The Final Report shall be written in a concise form and shall describe the major achievements of the Contract The Final Report may be made available to all ESA Participating States. Therefore, if the Final Report includes commercially sensitive information, two (2) different versions of the Final Report shall be provided. The front cover of the Final Report shall contain the following text: “EUROPEAN SPACE AGENCY CONTRACT REPORT “The work described in this report was done under ESA contract. Responsibility for the contents resides in the author or organization that prepared it.” | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
Engineering
S.EN1 | User/Customer Needs and Requirements | UCNR | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | template available at https://incubed.esa.int/list-documents/ | Use only paragraph 2 of the RD template (2. User/Customer Needs and Requirements). These requirments shall then have a tracebility with the MRD
S.EN2 | Technical Requirements Specification/ Product Specification | TRS | Yes | Yes | N | U | U | U | U |  | U | U |  | U | U |  |  | C | C |  | ECSS-E-ST-10-06C, Annex A | For lower levels as well, if applicable. May be merged with S.EN1
S.EN3 | Requirements Traceability Matrix | RTM | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10C, Annex N | If applicable. May be merged with S.EN2
S.EN4 | Verification Control Document | VCD | Yes | Yes |  | N | U | U |  |  | U | U |  | U | U |  |  | C | C |  | ECSS-E-ST-10-02C, Annex B | May be merged with S.EN2
S.EN5 | Compliance Matrix to Technical Specification | CMTS | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | Self descriptive | May be merged with S.EN2
S.EN6 | Design Verification Compliance Matrix | DVCM | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10-02C, Annex B | May be merged with S.EN2
S.EN7 | Specification tree | ST | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10C, Annex J | If applicable.
S.EN8 | Design Definition File | DDF | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10C, Annex G
S.EN9 | Design Justification File | DJF | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10C, Annex K
S.EN10 | Part drawings | PD | Yes | Yes |  |  | N | U |  |  | U | U | U | U | U |  |  | C | C |  | Self descriptive | May be available for on-site review only.
S.EN11 | Assembly drawings | AD | Yes | Yes |  |  | N | U |  |  | U | U | U | U | U |  |  | C | C |  | Self descriptive | May be available for on-site review only.
S.EN12 | Interface Control Document | ICD | Yes | Yes |  | N | U | U |  |  | U | U | U | U | U |  |  | C | C |  | ECSS-E-ST-10-24C, Annex C
S.EN13 | User Manual | UM | No | Yes | [16 empty] | ECSS-E-ST-10C, Annex P | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR to Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control SAT; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.EN14 | Trade-Off Report | TOR | Yes | Recommended | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10C, Annex L | If applicable.
S.EN15 | Performance Analyses | PA | Yes | Yes | N | U | U | U |  |  | U | U |  |  |  |  | U | C | C |  | ECSS-E-ST-10C, Annex Q | For instance: worst-case performance, power budget, leakage, gauging, sloshing, motorization, kinematics. May be merged with S.EN9 in one single document.
S.EN16 | Environmental Analyses | EA | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control SAT: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10C, Annex Q | For instance: thermal, mechanical, thermo-elastic, fatigue, fracture, EMC, ESD, venting, plume effects, corona. May be merged with S.EN9 in one single document.
S.EN17 | Mathematical Models | MM | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-31C, Annex B for thermal | E.g. performance, thermal, mechanical.
ECSS-E-ST-32C, Annex A for CAD
ECSS-E-ST-32C, Annex I for mechanical
ECSS-E-ST-35C Annex I for propulsion
ECSS-E-ST-60-20C, Annex A for star sensor
S.EN18 | Satellite level accommodation report | SLAR | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | Self descriptive | For Flying Items: for instance, accommodation studies, design modifications performed to accommodate the innovative product, any hardware specifically required for accommodation purposes and satellite level AIT, specific activities related to the innovative product during the AIT and launch campaigns.
S.EN19 | Statement of compliance to the Specifications | SCS | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | Self descriptive | Applicable only if multiple specifications are used.
S.EN20 | Technical Budgets | TB | Yes | Yes | N | U | U | U |  |  | U | U |  | U | U |  |  | C | C |  | ECSS-E-ST-10C, Annex I | May be merged with Design Definition File
Testing
S.TE1 | Assembly, Integration and Test Plan | AITP | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10-03C, Annex A
S.TE2 | Test Specification | TSPE | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10-03C, Annex B | Test procedures may be available for on-site review only.
S.TE3 | Test Procedure | TPRO | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10-03C, Annex C
S.TE4 | Test Report | TRPT | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRB: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control SAT: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10-03C, Annex C
S.TE5 | AIT report | AITR | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRB: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-10-03C, Annex C
S.TE6 | Satellite AIT report | SAITR | No | Yes | [16 empty] | ECSS-E-ST-10-03C, Annex C | with flight opportunity | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.TE7 | In-Orbit Test plan | IOTP | No | Yes | [16 empty] | ECSS-E-ST-10-03C, Annex A | with flight opportunity | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.TE8 | IOT report | IOTR | No | Yes | [16 empty] | ECSS-E-ST-10-03C, Annex C | with flight opportunity | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CRR; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.TE9 | In-orbit operation data gathering plan | IOODGP | No | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  |  | with flight opportunity
S.TE10 | In-orbit operation data report | IODR | No | Yes | [17 empty] | with flight opportunity | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control SAT; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.TE11 | Validation Plan | VP | No | Yes | [16 empty] | template available at https://incubed.esa.int/list-documents/ | With Validation Activities (a Pilot with the users/customers e.g. providing them L2/L3/L4 data products and getting their feedback) after the end of the commisioning phase (e.g. at IOCR) 1) Describe the entities involved in the operational use of the product (e.g. users/customers), at CDR 2) identify their role during the validation activities (a confirmation from them of their agreement to participate shall be provided in the proposal), at CDR 3) describe the approach to evaluate the success of the validation activities (e.g. identify measurable KPIs derived from on agreed validation activities objectives) at CRR or SAT and start the pilot activities 4)Results of the validation activities, Intermediate reports shall be delivered on a weekly basis during the pilot (validation) activity providing visibility on the measures of the agreed KPIs (usually gathered from/with users) at FR | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control SAT; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
Product Assurance
S.PA1 | Quality Assurance Plan | QAP |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-20C, Annex A
S.PA2 | Critical Item List | CIL | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-10-04C, Annex A
S.PA3 | Configuration Item Data List | CIDL |  | Yes |  |  | N | U | U |  | U | U | U | U | U |  |  |  | C |  | ECSS-M-ST-40C, Annex C
S.PA4 | As-built Configuration List | ABCL |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-M-ST-40C, Annex D | To be included in S.PA27 at AR. Required at TRR only for QM, PFM or FM.
S.PA5 | Qualification Status List | QSL | Yes | Yes |  |  | N | U | U |  | U | U |  | U | U |  |  | C | C |  | ECSS-Q-ST-10C, Annex B
S.PA6 | Manufacturing and inspection flow chart |  | Yes | Yes |  |  | N | U |  |  | U | U | U | U | U |  |  | C | C |  | ECSS-Q-ST-20C, Req. 5.5.1a – 5.5.1e | Includes MIP / KIP List (List of Inspections).
S.PA7 | Declared Materials List | DML | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-70C, Annex A
S.PA8 | Declared Mechanical Parts List | DMPL | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-70C, Annex B | May be merged with S.PA7
S.PA9 | Declared Processes List | DPL | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-70C, Annex C | May be merged with S.PA7
S.PA10 | Declared Components List | DCL | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-60C, Annex B
S.PA11 | Part Approval Document | PAD |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-60C, Annex D | PAD only required as defined in the Product Quality Requirements.
S.PA12 | Cleanliness and contamination control plan | CCCP |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-70-01C, Annex B | If required Product Quality Requirements.
S.PA13 | Failure Mode Effects and Criticality analysis | FMECA | Yes | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-30-02C, Annex A
S.PA14 | Worst-Case Analysis | WCA |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-30C, Annex J | If applicable.
S.PA15 | Reliability assessment report | RAR |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-30C, Annex E
S.PA16 | Availability analysis | AA |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-30-09C, Req. 6.4 | May be merged with S.PA15
S.PA17 | Maintainability analysis | MA |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-30C, Annex H | May be merged with S.PA15
S.PA18 | Safety analysis | SA |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-40C, Annex C | May be merged with S.PA15
S.PA19 | Part stress analysis | PSA |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-30-11C | If applicable
S.PA20 | Radiation analysis | RA | Recommended | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-60-15C, Annex B | May be merged with S.EN9
S.PA21 | Request For Deviation | RFD |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-M-ST-40C, Annex I | To be delivered when raised.
S.PA22 | Request For Waiver | RFW |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-M-ST-40C, Annex J | To be delivered when raised.
S.PA23 | Non-Conformance Report | NCR |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: Within 48 hours of occurrence |  | ECSS-Q-ST-10-09C, Annex A | A Non-conformance Review Board (NRB) has to be held subsequently to any NCR. The corresponding NRB report shall be delivered after NCR closure.
S.PA24 | End-Item Data Package | EIDP |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-20C, Annex B | Template of EIDP may be released at CDR for review.
ECSS-Q-ST-20C, Annex C | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
ECSS-Q-ST-20C, Annex D | bar: Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR
S.PA25 | Single Event Phenomena Rates Calculation | SEPRC |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-60-15C, Annex B | If applicable.
S.PA26 | Handling, Packing, Storage, and Transportation | HPST |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | Self descriptive
S.PA27 | RFD / RFW List | RFD-RFW |  | Yes | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | Self descriptive | Status list of all RFW / RFD.
Software
S.SW1 | Software Configuration File | SCF | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-M-ST-40C, Annex E | If applicable.
S.SW2 | Software Product Assurance Plan | SPAP | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-Q-ST-80C, Annex B | If applicable.
S.SW3 | Software Requirements Specification | SRS | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex D | If applicable.
S.SW4 | Software Interface Control Document | SICD | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex E | If applicable.
S.SW5 | Software Design Document | SDD | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex F | If applicable.
S.SW6 | Software Release Document | SrelD |  | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex G | If applicable.
S.SW7 | Software User Manual | SUM |  | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex H | If applicable.
S.SW8 | Software Verification Plan | SVerP | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex I | If applicable.
S.SW9 | Software Validation Plan | SValP | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex J | If applicable.
S.SW10 | Software Unit or Integration Test Plan | SUITP | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex K | If applicable.
S.SW11 | Software Validation Specification | SVS |  | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex L | If applicable.
S.SW12 | Software Verification Report | SVR |  | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control TRB: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control EQSR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control QR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PAR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control AR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex M | If applicable.
S.SW13 | Software Development Plan | SDP | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control MTR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-E-ST-40C, Annex O | If applicable.
S.SW14 | Software Configuration Management Plan | SCMP | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control RR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  | ECSS-M-ST-40C, Annex A | If applicable.
S.SW15 | Software Reuse File | SRF | Yes, If applicable | Yes, If applicable | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control PDR: N; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control CDR: U; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control DCCR: C; Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control FR: C |  |  | The Software Reuse File, if relevant, shall contain an analysis of existing software intended to be reused. The SRF shall be composed of the following two sections: Section 1, dedicated to present the analysis carried out to decide about the reuse (or not) of existing software taking into account the technical, operational and commercial requirements of the project. Furthermore the analysis shall cover the way the reused software will be embedded and/or integrated with the software to be developed in the project. The reused software shall be described in accordance with the information listed below (SRF List). Section 2, to characterize the deliverable software in terms of its constituent elements and the associated licensing schemes. The deliverable software (i.e. including developed and existing reused software) shall be described in accordance with the information listed below (SRF List): • software item name and main features; • developer name; • considered version and list of components; • licensing conditions; e.g. industrial property and exportability constraints, if any; • implementation language; • development and execution environment (e.g. platform, operating system); • applicable dispositions for warranty, maintenance, installation and training; • commercial software necessary for software execution, if any; • size of the software (e.g. number of source code lines, and size of the executable code)

## Ground Segment
Document |  |  | To be delivered in the cycle? (yes, yes, if applicable, no) |  | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control | [6 empty] | Document definition reference | Comments
Reference | Title | Acronym | De-risking | Product Development | RR | PDR | CDR | FAT | SAT | DCCR | FR
Management
G.MG1 | Configuration and Documentation Management Plan | CMDP | Yes | Yes | N | U |  |  |  | C | C | ECSS-M-ST-40C, Annex A
G.MG2 | Risk Register | RR | Yes | Yes | Monthly in the MPR and at each progress meeting | [6 empty] | ECSS-M-ST-80C, Annex D
G.MG3 | Business Plan | BP | Yes | Yes | N | U | U | U | U | U | U | template available at https://incubed.esa.int/list-documents/
G.MG4 | Document List | DL | Yes | Yes | N | U | U | U | U | C | C | Self descriptive | List of all documents produced in the frame of the contract.
G.MG5 | Monthly Progress Report | MPR | Yes | Yes | Monthly | [6 empty] | template available at https://incubed.esa.int/list-documents/ | A concise monthly progress report will be provided to the Agency within before the end of each month.
G.MG6 | Minutes of the Meeting | MoM | Yes | Yes | N | N | N | N | N | N | N | template available at https://incubed.esa.int/list-documents/ | Formal written minutes of meetings attended by the Agency will be agreed and, as far as possible, be signed and made available to the Agency at the end of the meeting. If this is not possible the minutes will be provided to the Agency no later than five working days from the date of the meeting. The minutes will, as a minimum, identify all agreements made and actions accepted during the meeting. The action item list will be included in the minutes and will be updated in accordance with the meeting outcome. Each action item will be assigned a unique identifier in the format X.Y, where X is the meeting number in which it originated and Y is the action number, starting from 1 at each meeting.
G.MG7 | Activity Web Page | AWP | Yes | Yes | At the first review meeting and current status updated at each progress meeting | [6 empty] | template available at https://incubed.esa.int/list-documents/ | As part of the first review data package the Contractor shall produce a Activity Web Page which shall be suited for publication by ESA in the InCubed web site. As a minimum, an update of the paragraph called “Current Status” shall be provided at each milestone review together with the minutes of the review meeting. A final version of the Activity Web Page shall be provided together with the Final Report. This final version shall include a paragraph summarising the most significant achievements of the activity.
G.MG8 | Justification for non continuation | JFNC | Yes, if applicable | No | [5 empty] | N |  |  | In the event that it is no longer proposed to continue with the development at the De-risking Cycle, the Contractor shall deliver a Justification Letter to the Agency. The Justification Letter shall set out the reasons (technical and/or commercial) for not continuing the development.
G.MG9 | Digital Media | DM | Yes | Yes | [5 empty] | N | N |  | High-Resolution (>2 MB) Photographs or a video shall be delivered, shall be releasable to the public and shall be delivered in a format that can easily be processed electronically (e.g. not in PDF).
G.MG10 | Product Data Sheet | PDS | No | Yes | [6 empty] | N |  | A Product Data Sheet shall be issued: • For each hardware unit which has been developed and tested within the contract, providing the functional performances, budgets (for space: mass, power, volume) and environmental specifications. • For each software item which has been developed and tested within the contract, listing the main functions and the demonstrated performance parameters.
G.MG11 | CCN for follow-on Cycle(s) | CCN-FOC | Yes | No | [5 empty] | N |  | template available at https://incubed.esa.int/list-documents/
G.MG12 | Contract Achievements and Socio Economic Impact Questionnaire | CA-SEIQ | No | Yes | [5 empty] | N | N | Online questionnaire to be provided by the TO | It will be provided at the end of the contract and will contain: summary of the activities, technical and commercial achievement, a socio-economic impact assessment of the activity. Once a year for 5 years after the conclusion of the contract the Agency will send an online questionnaire to be filled in to monitor the commercial growth of the product developed
G.MG13 | Final Data Package | FDP | Yes | Yes | [5 empty] | N | N |  | Comprise a compilation of the most recent versions of all deliverable documents including Final Report
G.MG14 | Final Report | FREP | Yes | Yes | [5 empty] | N | N | template available at https://incubed.esa.int/list-documents/ | The Final Report shall be written in a concise form and shall describe the major achievements of the Contract The Final Report may be made available to all ESA Participating States. Therefore, if the Final Report includes commercially sensitive information, two (2) different versions of the Final Report shall be provided. The front cover of the Final Report shall contain the following text: “EUROPEAN SPACE AGENCY CONTRACT REPORT “The work described in this report was done under ESA contract. Responsibility for the contents resides in the author or organization that prepared it.”
Engineering
G.EN1 | Requirement Document | RD | Yes | Yes | N | U | U |  |  | C | C | template available at https://incubed.esa.int/list-documents/
G.EN2 | Design Document | DD | Yes | Yes |  | N | U | U |  | C | C | template available at https://incubed.esa.int/list-documents/
G.EN3 | User Manual | UM | No | Yes |  |  |  |  | N |  | C
Testing
G.TE1 | Verification Document | VD | Yes | Yes |  | N | U | U | U | C | C | template available at https://incubed.esa.int/list-documents/ | Test Plan and Procedure at PDR and CDR; Test reports at FAT and at SAT
G.TE2 | Validation Plan | VP | No | Yes |  |  | N | U | U |  | U | template available at https://incubed.esa.int/list-documents/ | With Validation Activities 1) Describe the entities involved in the operational use of the product (e.g. users/customers), at CDR 2) identify their role during the validation activities (a confirmation from them of their agreement to participate shall be provided in the proposal), at CDR 3) describe the approach to evaluate the success of the validation activities (e.g. identify measurable KPIs derived from on agreed validation activities objectives) at FAT or SAT 4)Results of the validation activities, Intermediate reports shall be delivered on a weekly basis during the pilot (validation) activity providing visibility on the measures of the agreed KPIs (usually gathered from/with users) at FR
Product Assurance
G.PA1 | Quality Asssurance Plan | QAP | Recommended | Recommended |  | N | U | U |  | C | C | ECSS-Q-ST-10C, Annex A
Software
D.SW1 | Software Reuse File | SRF | Yes, if applicable | Yes, if applicable |  |  | N | U |  | C | C |  | The Software Reuse File, if relevant, shall contain an analysis of existing software intended to be reused. The SRF shall be composed of the following two sections: Section 1, dedicated to present the analysis carried out to decide about the reuse (or not) of existing software taking into account the technical, operational and commercial requirements of the project. Furthermore the analysis shall cover the way the reused software will be embedded and/or integrated with the software to be developed in the project. The reused software shall be described in accordance with the information listed below (SRF List). Section 2, to characterize the deliverable software in terms of its constituent elements and the associated licensing schemes. The deliverable software (i.e. including developed and existing reused software) shall be described in accordance with the information listed below (SRF List): • software item name and main features; • developer name; • considered version and list of components; • licensing conditions; e.g. industrial property and exportability constraints, if any; • implementation language; • development and execution environment (e.g. platform, operating system); • applicable dispositions for warranty, maintenance, installation and training; • commercial software necessary for software execution, if any; • size of the software (e.g. number of source code lines, and size of the executable code)

## Data Segment
Document |  |  | To be delivered in the cycle? (yes, yes, if applicable, no) |  | Review Data Package N: New issue to be delivered at the indicated review U: Updated issue to be delivered at the indicated review C: Document already delivered and under configuration control | [5 empty] | Document definition reference | Comments
Reference | Title | Acronym | De-risking | Product Development | RR | CDR | FAT | SAT | DCCR | FR
Management
D.MG1 | Risk Register | RR | Yes | Yes | Monthly in the MPR and at each progress meeting | [5 empty] | ECSS-M-ST-80C, Annex D
D.MG2 | Business Plan | BP | Yes | Yes | N | U | U | U | U | U | template available at https://incubed.esa.int/list-documents/
D.MG3 | Document List | DL | Yes | Yes | N | U | U | U | U | U | Self descriptive | List of all documents produced in the frame of the contract.
D.MG4 | Monthly Progress Report | MPR | Yes | Yes | Monthly | [5 empty] | template available at https://incubed.esa.int/list-documents/ | A concise monthly progress report will be provided to the Agency within before the end of each month.
D.MG5 | Minutes of the Meeting | MoM | Yes | Yes | N | N | N | N | N | N | template available at https://incubed.esa.int/list-documents/ | Formal written minutes of meetings attended by the Agency will be agreed and, as far as possible, be signed and made available to the Agency at the end of the meeting. If this is not possible the minutes will be provided to the Agency no later than five working days from the date of the meeting. The minutes will, as a minimum, identify all agreements made and actions accepted during the meeting. The action item list will be included in the minutes and will be updated in accordance with the meeting outcome. Each action item will be assigned a unique identifier in the format X.Y, where X is the meeting number in which it originated and Y is the action number, starting from 1 at each meeting.
D.MG6 | Activity Web Page | AWP | Yes | Yes | At the first review meeting and current status updated at each progress meeting | [5 empty] | template available at https://incubed.esa.int/list-documents/ | As part of the first review data package the Contractor shall produce a Activity Web Page which shall be suited for publication by ESA in the InCubed web site. As a minimum, an update of the paragraph called “Current Status” shall be provided at each milestone review together with the minutes of the review meeting. A final version of the Activity Web Page shall be provided together with the Final Report. This final version shall include a paragraph summarising the most significant achievements of the activity.
D.MG7 | Justification for non continuation | JFNC | Yes, if applicable | No |  |  |  |  | N |  |  | In the event that it is no longer proposed to continue with the development at the De-risking Cycle, the Contractor shall deliver a Justification Letter to the Agency. The Justification Letter shall set out the reasons (technical and/or commercial) for not continuing the development.
D.MG8 | Digital Media | DM | Yes | Yes |  |  |  |  | N | N |  | High-Resolution (>2 MB) Photographs or a video shall be delivered, shall be releasable to the public and shall be delivered in a format that can easily be processed electronically (e.g. not in PDF).
G.MG9 | Product Data Sheet | PDS | No | Yes | [7 empty] | A Product Data Sheet shall be issued: • For each hardware unit which has been developed and tested within the contract, providing the functional performances, budgets (for space: mass, power, volume) and environmental specifications. • For each software item which has been developed and tested within the contract, listing the main functions and the demonstrated performance parameters.
D.MG10 | CCN for follow-on Cycle(s) | CCN-FOC | Yes | No |  |  |  |  | N |  | template available at https://incubed.esa.int/list-documents/
D.MG11 | Contract Achievements and Socio Economic Impact Questionnaire | CA-SEIQ | No | Yes |  |  |  |  | N | N | Online questionnaire to be provided by the TO | It will be provided at the end of the contract and will contain: summary of the activities, technical and commercial achievement, a socio-economic impact assessment of the activity. Once a year for 5 years after the conclusion of the contract the Agency will send an online questionnaire to be filled in to monitor the commercial growth of the product developed
D.MG12 | Final Data Package | FDP | Yes | Yes |  |  |  |  | N | N |  | Comprise a compilation of the most recent versions of all deliverable documents including Final Report
D.MG13 | Final Report | FREP | Yes | Yes |  |  |  |  | N | N | template available at https://incubed.esa.int/list-documents/ | The Final Report shall be written in a concise form and shall describe the major achievements of the Contract The Final Report may be made available to all ESA Participating States. Therefore, if the Final Report includes commercially sensitive information, two (2) different versions of the Final Report shall be provided. The front cover of the Final Report shall contain the following text: “EUROPEAN SPACE AGENCY CONTRACT REPORT “The work described in this report was done under ESA contract. Responsibility for the contents resides in the author or organization that prepared it.”
Engineering
D.EN1 | Requirement Document | RD | Yes | Yes | N | U |  |  | C | C | template available at https://incubed.esa.int/list-documents/
D.EN2 | Design Document | DD | Yes | Yes |  | N | U |  | C | C | template available at https://incubed.esa.int/list-documents/
D.EN3 | User Manual | UM | No | Yes |  |  |  | N |  | C
Testing
D.TE1 | Verification Document | VD | Yes | Yes |  | N | U | U | C | C | template available at https://incubed.esa.int/list-documents/ | Test Plan and Procedure at CDR; Test reports at FAT and at SAT
D.TE2 | Validation Plan | VP | No | Yes |  | N | U | U |  | U | template available at https://incubed.esa.int/list-documents/ | With Validation Activities 1) Describe the entities involved in the operational use of the product (e.g. users/customers), at CDR 2) identify their role during the validation activities (a confirmation from them of their agreement to participate shall be provided in the proposal), at CDR 3) describe the approach to evaluate the success of the validation activities (e.g. identify measurable KPIs derived from on agreed validation activities objectives) at FAT or SAT 4)Results of the validation activities, Intermediate reports shall be delivered on a weekly basis during the pilot (validation) activity providing visibility on the measures of the agreed KPIs (usually gathered from/with users) at FR
Product Assurance
D.PA1 | Quality Asssurance Plan | QAP | Recommended | Recommended |  | N |  |  | U | C | ECSS-Q-ST-10C, Annex A
Software
D.SW1 | Software Reuse File | SRF | Yes, if applicable | Yes, if applicable |  | N | U |  | C | C |  | The Software Reuse File, if relevant, shall contain an analysis of existing software intended to be reused. The SRF shall be composed of the following two sections: Section 1, dedicated to present the analysis carried out to decide about the reuse (or not) of existing software taking into account the technical, operational and commercial requirements of the project. Furthermore the analysis shall cover the way the reused software will be embedded and/or integrated with the software to be developed in the project. The reused software shall be described in accordance with the information listed below (SRF List). Section 2, to characterize the deliverable software in terms of its constituent elements and the associated licensing schemes. The deliverable software (i.e. including developed and existing reused software) shall be described in accordance with the information listed below (SRF List): • software item name and main features; • developer name; • considered version and list of components; • licensing conditions; e.g. industrial property and exportability constraints, if any; • implementation language; • development and execution environment (e.g. platform, operating system); • applicable dispositions for warranty, maintenance, installation and training; • commercial software necessary for software execution, if any; • size of the software (e.g. number of source code lines, and size of the executable code)